## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Setup Data Ingestion & Preprocessing Pipeline (Clean Enron Data) | MUST HAVE | None | Sabaridev K | Completed
S2 | S2 | US-002 | Design & Deploy Neo4j Knowledge Graph (Nodes & Edges) | MUST HAVE | US-001 | Sabaridev K | Completed
S3 | S3 | US-003 | Build Vector Store (Pinecone) & Semantic Embeddings | MUST HAVE | US-001 | Sabaridev K | Completed
S4 | S4 | US-004 | Develop & Deploy Interactive Streamlit Intelligence Dashboard | MUST HAVE | US-002, US-003 | Sabaridev K | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Estimate (Hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1: DATA PREPROCESSING
US-001 | T-001 | Load Enron dataset and parse JSON objects | Day 1 | Day 3 | Sabaridev K | Dev | Done | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Clean data, handle NaNs, filter metadata | Day 3 | Day 6 | Sabaridev K | Dev | Done | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-003 | Export processed text to clean CSV | Day 6 | Day 7 | Sabaridev K | Dev | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 Totals | [7 empty] | 14 | 14 | 12 | 9 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2: KNOWLEDGE GRAPH
US-002 | T-004 | Set up Neo4j AuraDB instance & auth | Day 1 | Day 2 | Sabaridev K | DBA | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-005 | Write Cypher queries for Nodes/Edges | Day 2 | Day 5 | Sabaridev K | Dev | Done | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-006 | Batch upload processed CSV to Neo4j | Day 5 | Day 7 | Sabaridev K | Dev | Done | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 Totals | [7 empty] | 17 | 17 | 13 | 9 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3: VECTOR SEARCH
US-003 | T-007 | Initialize HuggingFace Embeddings | Day 1 | Day 2 | Sabaridev K | AI | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-008 | Configure Pinecone Index and Vector DB | Day 2 | Day 4 | Sabaridev K | DBA | Done | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-009 | Upsert vectors & metadata to Pinecone | Day 4 | Day 7 | Sabaridev K | Dev | Done | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 Totals | [7 empty] | 16 | 16 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4: STREAMLIT DASHBOARD
US-004 | T-010 | Build LangChain Hybrid RAG Engine | Day 1 | Day 4 | Sabaridev K | Dev | Done | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-011 | Develop UI layout and Search Bar | Day 4 | Day 8 | Sabaridev K | UI/UX | Done | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-012 | Render Plotly/NetworkX Graph & KPIs | Day 8 | Day 12 | Sabaridev K | Dev | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0
US-004 | T-013 | Cloud deployment and Security Vault | Day 12 | Day 14 | Sabaridev K | DevOps | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
SPRINT 4 Totals | [7 empty] | 30 | 30 | 28 | 25 | 22 | 20 | 18 | 16 | 14 | 10 | 7 | 4 | 4 | 2 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 4 | JSON formats vary across files causing parsing errors. | Wrote custom logic to handle nested dictionaries.
S2 | Day 6 | Neo4j connection timing out during batch upload. | Implemented UNWIND Cypher query to process 2000 records at a time.
S3 | Day 5 | Pinecone rate limits hit during embedding upload. | Added time.sleep() delays and batching to respect free tier limits.
S4 | Day 11 | Streamlit UI resetting when a graph node is clicked. | Managed state properly using st.session_state cache.

## Retrospection
SL # | Sprint # | Start Date | End Date | Assignee | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | S1 | W1 | W2 | Sabaridev K | Validate data types before ingestion | Assuming data is perfectly clean | Writing modular Python scripts | Added schema validation layer
2 | S2 | W3 | W4 | Sabaridev K | Test small graph sets before big loads | Executing massive queries immediately | Using Neo4j AuraDB browser for tests | Created sample query test scripts
3 | S3 | W5 | W6 | Sabaridev K | Monitor vector dimensions strictly | Exceeding API limits | Utilizing SentenceTransformers | Enforced 384-dimension constraints
4 | S4 | W7 | W8 | Sabaridev K | Secure secrets before deployment | Hardcoding API keys | Focusing on clean UX | Migrated all keys to Streamlit Secrets